## Sponsor Inputs
# | High level ideas / Features
1 | Create Account
2 | View Restaurants
3 | Search Restaurants
4 | View Menu
5 | Add to Cart
6 | Purchase
7 | Restaurant views order
8 | Restaurant marks order as delivered
Notes:
1 | The above points were listed as draft ideas by the project sponsor.
2 | The project sponsor mentioned that he wants to compete against Talabat.
3 | As a sponsor, I am planning to compete against Talabat.
4 | This is a view only file, you can make a copy then edit in the copy.
5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
As a < type of user >, I want < some goal > so that < some reason >
| Create Account | AS a client User , I want to Create Account so that I can use the service | Heigh | 20 | 40 | Completed
| View Restaurants | As a client user I want to View Restaurants to determine which one the user can order from it | Heigh | 25 | 40 | Accepted
| Search Restaurants | AS a Sponsor I want to Search Restaurants to make it easy to user | Normal | 15 | 40 | Completed
| View Menu | As a User I want to View Menu to choose the food | Heigh | 30 | 40 | Completed
| Add to Cart | As a sponsor I want t user can add the order to Cart to pay | Heigh | 15 | 40 | In Progress
| Purchase | As a User I want to Purchase to my order | Normal | 20 | 40 | In Evaluation
| Restaurant views order | AS a sponsor I want Restaurant views order to supply them to the user | Heigh | 35 | 40 | Completed
| Restaurant marks order as delivered | AS a sponsor I wnat that Restaurant marks order as delivered when it’s done | Normal | 35 | 40 | Completed